**Week 1 Report (18 Jul 19 - 26 Jul 19)**

**Milestones**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S/No** | **Milestones** | **Start Date** | **End Date** | **Status** |
| 1 | Project Plan | 22 Jul 19 | 26 Jul 19 | Completed |
| 2 | UI Prototype | 19 Jul 19 | 25 Jul 19 | Completed |
| 3 | User Requirement Specification Document | 26 Jul 19 | 29 Jul 19 |  |
| 4 | Database Design (ER Diagram) | 30 Jul 19 | 01 Aug 19 |  |
| 5 | Source Codes | 02 Aug 19 | 20 Aug 19 |  |
| 6 | System User Guide | 14 Aug 19 | 16 Aug 19 |  |
| 7 | UAT Performance Test Plans | 14 Aug 19 | 16 Aug 19 |  |
| 8 | Conduct UAT | 19 Aug 19 | 19 Aug 19 |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

**Completed Tasks for This Week**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S/No** | **Tasks** | **Start Date** | **End Date** | **Status** |
| 1 | Produce Project Plan | 22 Jul 19 | 22 Jul 19 | Completed |
| 2 | Review/approve Project Plan | 23 Jul 19 | 23 Jul 19 | Completed |
| 3 | User Interview | 18 Jul 19 | 18 Jul 19 | Completed |
| 4 | Produce Functional Requirement | 19 Jul 19 | 22 Jul 19 | Completed |
| 5 | Final Review/Approve UI Prototype | 24 Jul 19 | 25 Jul 19 | Completed |

**Planned Tasks for Next Week**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S/No** | **Tasks** | **Start Date** | **End Date** | **Status** |
| 1 | Compile User Requirement Specification | 26 Jul 19 | 29 Jul 19 |  |
| 2 | Relational Database Design | 30 Jul 19 | 1 Aug 19 |  |
| 3 | Produce Database | 1 Aug 19 | 2 Aug 19 |  |
|  |  |  |  |  |
|  |  |  |  |  |

**Issues / Risks**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S/No** | **Issues / Risks** | **Impact** | **Owner** | **Target Date** |
| 1 | No Mobile UI Design for Stock Retrieval | Design Screen | Zhen Xiang | 26 July 2019 |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |