**Week 3 Report (05 Aug 19 - 08 Aug 19)**

**Milestones**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S/No** | **Milestones** | **Start Date** | **End Date** | **Status** |
| 1 | Project Plan | 22 Jul 19 | 26 Jul 19 | Completed |
| 2 | UI Prototype | 19 Jul 19 | 25 Jul 19 | Completed |
| 3 | User Requirement Specification Document | 26 Jul 19 | 29 Jul 19 | Completed |
| 4 | Database Design (ER Diagram) | 30 Jul 19 | 01 Aug 19 | Completed |
| 5 | Source Codes | 02 Aug 19 | 20 Aug 19 | In Progress |
| 6 | System User Guide | 14 Aug 19 | 16 Aug 19 | In Progress |
| 7 | UAT Performance Test Plans | 14 Aug 19 | 16 Aug 19 | In Progress |
| 8 | Conduct UAT | 19 Aug 19 | 19 Aug 19 |  |

**Completed Tasks for This Week**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S/No** | **Tasks** | **Start Date** | **End Date** | **Status** |
| 1 | Code Integration for Department | 02 Aug 19 | 05 Aug 19 | Completed |
| 2 | User Guide for Department | 06 Aug 19 | 07 Aug 19 | Completed |
| 3 | UAT Test Plan for Department | 07 Aug 19 | 08 Aug 19 | Completed |
| 4 | Start Development of Android Platform for Department | 08 Aug 19 | 13 Aug 19 | In Progress |
| 5 | Code Integration for Store | 08 Aug 19 | 13 Aug 19 | In Progress |

**Planned Tasks for Next Week**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S/No** | **Tasks** | **Start Date** | **End Date** | **Status** |
| 1 | Source Codes | 02 Aug 19 | 20 Aug 19 | In Progress |
| 2. | Complete Development of Android Platform for Department | 08 Aug 19 | 13 Aug 19 | In Progress |
| 3. | Complete Code Integration for Store | 08 Aug 19 | 13 Aug 19 | In Progress |
| 4 | Final Code Integration | 13 Aug 19 | 15 Aug 19 |  |
| 5 | User Guide for Store | 13 Aug 19 | 14 Aug 19 |  |
| 6 | UAT Test Plan for Store | 14 Aug 19 | 15 Aug 19 |  |
| 7 | UAT Test Plan for Department Android | 14 Aug 19 | 15 Aug 19 |  |
| 8 | Finalization of User Guides | 15 Aug 19 | 16 Aug 19 |  |

**Issues / Risks**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **S/No** | **Issues / Risks** | **Impact** | **Owner** | **Target Date** |
| 1 | Integration for Store | 2 Man-days to understand how each member wrote their part. | Zhen Xiang | 13 August |
| 2 | Conversion of Store in Web to responsive | 2 Man-days for research | Antonio, Zhen Xiang, Uday, Prashanth | 13 August |
| 3. | Final Code Integration | 2 Man | Kyaw | 15 August |
|  |  |  |  |  |
|  |  |  |  |  |